Updated Project Plan (v2) — AffectDF-Anchored

Quantifying and Closing the Code-Mixing Generalisation Gap in Audio Deepfake Detection + Live Call Detection Demo

B.Tech CSE (Data Science), Semester 7 — Team L / M / SK  |  Plan revised: 12 August 2026 (start of Week 3)

# 1. Strategy: our position relative to the base paper

Base paper: AffectDF (Mahapatra et al., arXiv:2608.05507, Aug 2026) — the most comprehensive benchmark for emotionally expressive speech deepfake detection. It shows that SDD systems trained on conventional benchmarks collapse under distribution shift (e.g., AASIST: 0.83% EER in-domain to 56.40% on AffectDF), that retraining on the shifted domain gives inconsistent gains and damages conventional-benchmark performance, and it stops at measurement — no mitigation strategy is tested.

We do not compete with AffectDF on scale (260 hours, 21 attacks, A100/H100 clusters). We contribute on the axes it does not cover. Our value-over-baseline claim, stated once and defended everywhere:

"AffectDF measures the emotional generalisation gap and stops. We measure the code-mixing gap under channel-matched telephony conditions — and then close it, and deploy it live."

## 1.1 Gap-contribution map (their gap, our contribution)

| AffectDF gap / omission | Our contribution |
| --- | --- |
| Entirely English (ESD + MSP-Podcast); no code-mixed or non-English speech | Hinglish code-mixed axis: gap matrix across English / mono-Hindi / mono-Tamil / code-mixed columns — headline result |
| Measures failure only; no mitigation tested | 3-system comparison: S1 English-only (gap) -> S2 LoRA-adapted (cheap fix) -> S3 native code-mixed (ceiling) |
| Clean-condition audio; no telephony/codec simulation | Channel-matched protocol: 8 kHz AMR-NB/G.711 + SNR noise on every eval cell, clean copies retained |
| No system/deployment component | Live Twilio call detection: beep in receiver ear, dashboard, SMS escalation — the protocol deployed |
| Emotion-wise slicing (their Table 3) | Our analogue: switch-density slicing + read vs spontaneous (HiACC) fixed-tool contrast |
| Their finding: domain retraining wrecks conventional performance | We test the same trade-off on our axis: does S3 lose English performance where S2 (LoRA) preserves it? |

Methodology we adopt from AffectDF (makes our paper look mature): attack-ID taxonomy table with disjoint speakers AND disjoint attack systems across splits; rich per-clip protocol files; the low-level-cue logistic-regression shortcut check (their Appendix G); fixed-generator style-contrast design; min t-DCF alongside EER where applicable; and zero-shot cross-evaluation of our systems on an AffectDF test subset (CC BY-NC 4.0) as an external benchmark column.

# 2. Where we are (12 Aug 2026)

- Weeks 1–2 code is written and pushed on per-task branches (repo scaffold, download scripts, preprocessing, channel sim, dataset/metrics modules, WebRTC harness, pool-carving code).

- Blocked human gates, in order: (1) review + merge the 4 open PRs; (2) mentor ethics sign-off (nothing generates before this); (3) run the MUCS + HiACC downloads and preprocessing; (4) channel-sim listening test; (5) speaker selection + pool freeze.

- Timeline: 10 weeks remain (Weeks 3–12). Spoof generation is the critical path and it sits behind the gates above. Clear them inside Week 3 or every downstream week slips.

# 3. The three systems (unchanged)

| System | Definition | Role in the paper |
| --- | --- | --- |
| S1 | wav2vec2/WavLM fine-tuned on ASVspoof 2019 LA only (zero code-mixed exposure) | Establishes the gap; anchors us to published literature |
| S2 | S1 + LoRA adaptation on the disjoint code-mixed adaptation pool (~1% trainable params) | The cheap fix; the mitigation AffectDF never tested |
| S3 | Trained directly on MUCS/HiACC bonafide + XTTS/RVC clones | The ceiling; also tested for reverse degradation on English |

Fallback rule (agreed now): if Kaggle hours run short, drop S3 ablations first, then S2 — never S1. If S1 fails its published-EER gate by end of Week 6, invert: anchor with pretrained AASIST/RawNet2 zero-shot on our eval set and reframe around cross-tool generalisation.

# 4. Week-by-week plan (Weeks 3–12)

## Week 3 (this week) — Unblock everything + AffectDF integration

Goal: every human gate cleared; base-paper positioning written; pilots rated.

| ID | Owner | Task | Pushed to GitHub by Sunday |
| --- | --- | --- | --- |
| W3-T1 | ALL | Clear the gates: each member reviews + merges one teammate's open PR (4 total); obtain mentor ethics sign-off on the REVISED scope (larger spoof volume, RVC added, AffectDF cross-eval); log-book entries for Weeks 1–2. | Merged PRs; docs/ethics/mentor_signoff.pdf |
| W3-T2 | L | Run MUCS + HiACC downloads; verify HiACC child quarantine against the real folder/manifest layout BY HAND; run preprocessing to 16 kHz segments; channel-sim listening test on 20 clips. | download logs + docs/qa/child_quarantine_check.md |
| W3-T3 | M | Deep-read AffectDF; write the related-work anchor + precise gap statement ("multilingual, channel, emotional shift covered; intra-utterance code-switching unexamined"); draft OUR attack-taxonomy table (attack IDs, tool, pool, split) in AffectDF Table-1 format. | docs/related_work_notes.md + docs/attack_taxonomy.md |
| W3-T4 | L+SK | Speaker selection: scripted SNR/duration ranking, team listening pass; select 30–50 adult speakers; freeze THREE disjoint pools (train / adaptation / eval) and commit. | data/manifests/speaker_pools.csv (frozen) |
| W3-T5 | SK | After sign-off: XTTS-v2 pilot (20 clips; test Devanagari vs romanised, hi vs en) + RVC pilot (1 speaker model, 10 conversions); team rates all 30, agrees quality bar. | notebooks/spoof_quality_audit.ipynb (pilot) |
| W3-T6 | M | Verify Kaggle GPU on all 3 accounts, W&B project, HF tokens/gated datasets; download ASVspoof 2019 LA for S1 (keep — S1 is the anchor). | notebooks/env_check.ipynb run + links in README |

Checkpoint: All gates cleared; pools frozen; pilots rated; AffectDF positioning committed. If sign-off has not happened by Wednesday, escalate to the mentor in person.

## Week 4 — Spoof generation at scale (now the core data contribution)

Goal: the full code-mixed spoof corpus, train + eval + held-out, with AffectDF-grade metadata.

| ID | Owner | Task | Pushed to GitHub by Sunday |
| --- | --- | --- | --- |
| W4-T1 | L | XTTS-v2 generation at scale from generation_jobs.csv: train-pool speakers, ~4,000+ utterances targeting rough parity with bonafide hours; idempotent/resumable; per-clip metadata (tool, version, speaker, reference, transcript, settings, pool). | src/data/spoof_generation.py + metadata CSV |
| W4-T2 | SK | RVC track: train per-speaker models for 10–15 train-pool targets (overnight batches); convert same-pool source utterances; log source + target + model checksum. | src/data/rvc_generation.py + metadata |
| W4-T3 | SK | Held-out attacks, eval-pool speakers only: Tortoise-TTS 400–600 utterances (+ optionally kNN-VC); firewalled directory; never in any training manifest. | data/generated/heldout_tool/ metadata |
| W4-T4 | M | Model modules (encoder wrapper, attentive stats pooling, MLP head) + training loop (AMP, checkpointing, resume-from-latest, W&B); smoke-test on 1% of the new data. | src/models/ + src/training/train.py + smoke run |
| W4-T5 | M | Rewrite anti-leakage suite for the new regime: speaker-pool disjointness (incl. cloned voices AND RVC source/target), tool firewall, transcript near-duplicates, no child audio; wire into CI. | tests/test_splits.py passing in CI |
| W4-T6 | L | Quality audit: auto-filters (duration mismatch, near-silence, clipping) + 50-clip listening per member + ECAPA-TDNN speaker-similarity and Whisper transcript-check statistics. | audit report + stats in notebook |

Checkpoint: Full spoof corpus generated with metadata; audit statistics documented; leakage tests green.

## Week 5 — Dataset v1 freeze + S1/S3 launched in parallel

| ID | Owner | Task | Pushed to GitHub by Sunday |
| --- | --- | --- | --- |
| W5-T1 | L | Assemble Dataset v1: manifests for all four eval columns (English / mono-Hindi / mono-Tamil / code-mixed), identical channel simulation on all eval audio, clean copies retained; FREEZE with changelog. | src/data/build_manifests.py + manifests |
| W5-T2 | L | Dataset datasheet in AffectDF style: attack-taxonomy table, per-corpus licences, generation process, exclusions, spoof:real ratios per split. | docs/datasheet.md |
| W5-T3 | M | Launch S1 (ASVspoof baseline) on account 1 and S3 (code-mixed native) on account 2, in parallel; iterate LR/schedule; all runs in W&B. | configs + W&B runs + checkpoints on Kaggle Datasets |
| W5-T4 | M | AffectDF Appendix-G replica: logistic regression on 8 low-level signal features (RMS, clipping, ZCR, rolloff, etc.) over OUR dataset — must be near chance, else fix the pipeline before trusting anything. | experiments/results/lowlevel_cue_check.json |
| W5-T5 | SK | FastAPI server skeleton + streaming windowing prototype (4 s window / 2 s hop over faked stream). | live_call/server.py + src/inference/streaming.py |
| W5-T6 | ALL | Review 1 package (if scheduled): dataset statistics, taxonomy table, pipeline diagram, pilot results, AffectDF positioning slide. | report/presentation/review1.pptx |

Checkpoint: Dataset v1 FROZEN. S1 and S3 training in progress. Low-level-cue check passed (near-chance).

## Week 6 — Validation gates (trust before numbers)

| ID | Owner | Task | Pushed to GitHub by Sunday |
| --- | --- | --- | --- |
| W6-T1 | M | S1 GATE: EER on ASVspoof held-out eval must land in a defensible published range. If off, debugging takes priority over everything. | experiments/results/baseline.json |
| W6-T2 | M | S3 GATE: sane EER on eval pool; near-0% on seen tools + collapse on unseen = shortcut learning — investigate (channel sim on training data? augmentation on?). | experiments/results/s3_validation.json |
| W6-T3 | L | Eval-set QA (speaker overlap zero, uniform channel sim, label balance) + slicing infrastructure: SNR bins, tool tags, switch-density annotation, read/spontaneous tags (HiACC). | docs/qa_report.md + notebooks/eda_corpora.ipynb |
| W6-T4 | SK | Streaming inference live over WebRTC harness (screen capture); ONNX export + int8; CPU latency benchmark (< 1.5 s per 4 s window). | demo capture + benchmark table |
| W6-T5 | ALL | Mid-project risk review: both gates status, GPU burn, Twilio window planning; adjust Weeks 7–9 scope; minutes committed. | docs/minutes/week6_risk_review.md |

Checkpoint: Both training gates passed (or contingency invoked). Streaming works on live audio.

## Week 7 — THE GAP MATRIX + reverse-degradation + Twilio live

| ID | Owner | Task | Pushed to GitHub by Sunday |
| --- | --- | --- | --- |
| W7-T1 | M | Run S1 unmodified on all four eval columns, clean AND channel-matched; EER/AUC/F1 per cell with bootstrap CIs; publication heatmap. This is the headline result, in hand by midterm. | experiments/gap_matrix/ + heatmap figure |
| W7-T2 | M | Reverse check (our version of AffectDF's key finding): evaluate S3 on English/ASVspoof eval — does native code-mixed training wreck conventional performance? | experiments/results/s3_reverse_degradation.json |
| W7-T3 | L | Slice gap-matrix results by SNR, attack tool (seen vs unseen), corpus, switch density; begin error analysis (which spoofs fool S1; which genuine code-mixed clips get falsely flagged). | notebooks/error_analysis.ipynb |
| W7-T4 | SK | ACTIVATE Twilio trial (30-day window covers Weeks 7–10): webhook -> Conference -> Media Streams tap -> websocket -> streaming inference; track 75-min budget from day one. | live_call/server.py + media_handler.py |
| W7-T5 | SK | End-to-end real-call test: dial in, play genuine + spoofed clips, log verdicts (terminal is fine). | verdict logs + short recording in docs/ |
| W7-T6 | ALL | Review 2 / midterm: gap matrix v1 + live terminal call demo + AffectDF comparison slide. | report/presentation/review2.pptx |

Checkpoint: Gap matrix v1 exists. A real phone call gets classified live. Reverse-degradation result recorded.

## Week 8 — S2 (LoRA) + AffectDF cross-eval + dashboard

| ID | Owner | Task | Pushed to GitHub by Sunday |
| --- | --- | --- | --- |
| W8-T1 | M | S2: LoRA/top-layer adaptation (PEFT) on the adaptation pool; re-evaluate on all columns (clean + channel, seen + unseen); verify English performance preserved; produce the 3-way S1/S2/S3 table draft. | configs/train_lora_codemix.yaml + adaptation.json |
| W8-T2 | M+L | External benchmark column: zero-shot S1/S2/S3 on a sampled AffectDF test subset (CC BY-NC; check size/practicality first) — "our models under emotional shift" cross-validates both papers and patches the self-generated-test-set weakness. | experiments/results/affectdf_crosseval.json |
| W8-T3 | L | Fixed-tool style contrast (their acted-vs-spontaneous move, our data): same generator, read vs spontaneous HiACC subsets; write up. | analysis section in error_analysis.ipynb |
| W8-T4 | SK | Receiver dashboard (live status, rolling verdict, confidence, timeline) + browser dialer; alert layer 1: warning beep/whisper into RECEIVER leg on threshold cross. | live_call/static/ + alerts.py |
| W8-T5 | L | Demo audio arsenal (10–15 verified clips through full Twilio path); operating threshold from DET curve, ALL sign off. | demo_assets/ + configs/threshold.yaml |

Checkpoint: 3-way table draft exists. AffectDF cross-eval done. Live call shows beep + red dashboard.

## Week 9 — Ablations, escalation, RESULTS FREEZE

| ID | Owner | Task | Pushed to GitHub by Sunday |
| --- | --- | --- | --- |
| W9-T1 | M | Primary ablation: XTTS-only vs XTTS+RVC training for S3 (does attack diversity improve unseen-tool EER?); secondary (frozen vs fine-tuned encoder) only if hours allow. | experiments/results/ablations.json |
| W9-T2 | M | Consolidate final tables + publication figures (gap heatmap, 3-way table, DET curves, cross-eval, reverse-degradation). | experiments/figures/ complete |
| W9-T3 | L | Complete error analysis by switch density, SNR, length, tool — written DIRECTLY as draft paper text; datasheet finalised as supplementary. | paper/sections/analysis.tex + supplementary |
| W9-T4 | SK | Escalation ladder (beep -> repeat + SMS -> call-end summary); Gradio demo on HF Spaces; persistent host deploy; decide Twilio pay-as-you-go top-up if viva falls outside trial. | verdict_engine.py + live Space URL |
| W9-T5 | ALL | RESULTS FREEZE meeting: these are the paper's numbers; later reruns only for logged bug fixes. | CHANGELOG.md freeze entry + minutes |

Checkpoint: All experimental results frozen. Both demos functional.

## Week 10 — Paper draft (full IEEE draft, internally reviewed)

| ID | Owner | Task | Pushed to GitHub by Sunday |
| --- | --- | --- | --- |
| W10-T1 | ALL | Venue shortlist DAY 1 (2–3 legitimate Scopus-indexed: INDICON/TENCON-class or Springer speech/AI); check deadlines; reorder Weeks 10–11 if a deadline forces it; predatory venues excluded. | docs/venues.md |
| W10-T2 | L | Write: Dataset & Corpus Construction (taxonomy table front and centre), Channel-Matched Protocol, Ethics/Licence statement. | paper/sections/ (L) |
| W10-T3 | M | Write: Methodology (S1/S2/S3), Experiments & Results (gap matrix, 3-way, cross-eval, low-level check, reverse degradation), all figures placed. | paper/sections/ (M) |
| W10-T4 | SK | Write: Introduction + Related Work ANCHORED ON AffectDF (they measure emotion, we measure code-mixing and close it), System & Deployment, Conclusion. | paper/sections/ (SK) |
| W10-T5 | M | REPRODUCE.md draft: configs + seeds + commands regenerating every table from checkpoints. | REPRODUCE.md (draft) |
| W10-T6 | ALL | Cross-review via PR comments; one full integration pass; main.tex compiles. | review comments resolved |

Checkpoint: Complete draft in Overleaf/repo, internally reviewed once.

## Week 11 — SUBMIT + demo polish + final matrix

| ID | Owner | Task | Pushed to GitHub by Sunday |
| --- | --- | --- | --- |
| W11-T1 | ALL | Mentor revision pass; plagiarism/AI-similarity check (< 10%); SUBMIT to chosen venue. Non-negotiable outcome of the week. | submission receipt + tagged version |
| W11-T2 | M | Final full evaluation matrix from frozen checkpoints; model freeze; archive checkpoints to Kaggle Datasets/Drive with hashes. | final_matrix.json + archive links |
| W11-T3 | SK | Demo polish + rehearsed 3-minute script; record the backup screen-recording WITH audio of a full successful run. | docs/viva/demo_script.md + recording |
| W11-T4 | L | Failure-case exhibit (5–6 curated successes AND honest failures, incl. switch-boundary examples); final licence/ethics package; Twilio spend check. | docs/viva/failure_cases.md + budget.md |
| W11-T5 | ALL | Department report skeleton in institute template; drop in reformatted paper content; assemble log-book entries. | report/report_draft.docx (~50%) |

Checkpoint: PAPER SUBMITTED. Final numbers locked. Backup recording exists. Report ~50%.

## Week 12 — Report, presentation, viva (Review 3)

| ID | Owner | Task | Pushed to GitHub by Sunday |
| --- | --- | --- | --- |
| W12-T1 | L | Report chapters: Introduction, Literature Survey (AffectDF-anchored), Dataset & Methodology (data half); complete log book. | report/ chapters + logbook |
| W12-T2 | M | Report chapters: Methodology (model half), Results & Analysis, all figures/tables; REPRODUCE.md fresh-clone test; tag v1.0. | report/ chapters + git tag |
| W12-T3 | SK | Report chapters: System Design (live-call architecture diagram), Conclusion; final presentation deck (each member presents their third); 3x dress rehearsal, issue filed per flaky behaviour. | report/ chapters + final.pptx |
| W12-T4 | ALL | Viva Q&A prep including the two anticipated hard questions: "How is this different from AffectDF?" and "Why trust results on self-generated spoofs?" (answers: complementary axis + mitigation + telephony + deployment; held-out tools + external cross-eval + low-level-cue check). | docs/viva/qa_prep.md |
| W12-T5 | ALL | Final report assembly, print, hard-bound submission; repo cleanup; tag v1.0-final. | final PDF + git tag v1.0-final |

Checkpoint: Review 3 done. Project complete.

# 5. The paper's claims table (write toward this from day one)

| Claim | Evidence that proves it | Produced in |
| --- | --- | --- |
| English-trained SDD fails on Hinglish telephony speech | Gap matrix: S1 EER per column, clean vs channel, with CIs | Week 7 |
| LoRA adaptation closes part of the gap cheaply | S1 vs S2 delta on all columns; English performance preserved | Week 8 |
| Native code-mixed training is the ceiling — at a cost | S3 results + reverse-degradation on English (mirrors AffectDF's finding) | Weeks 6–7 |
| Results are not shortcut artifacts | Low-level-cue check near chance; held-out-tool EER; channel sim on both classes | Weeks 5–6 |
| Results are not dataset-local | Zero-shot cross-eval on AffectDF subset + pretrained AASIST comparison row | Week 8 |
| The protocol works in the real world | Live Twilio call detection with latency numbers + demo recording | Weeks 7–9 |

# 6. Top risks (revised)

- Gates slip past Week 3. Ethics sign-off and downloads are human steps with no technical workaround; if not cleared by Wednesday of Week 3, escalate in person and compress Week 4 generation into split day/night sessions across all three accounts.

- S1 baseline does not reproduce (Week 6 gate). Contingency: anchor with pretrained AASIST/RawNet2 zero-shot rows; reframe around cross-tool generalisation. Decided in the Week 6 risk review, not later.

- Shortcut learning in S3. Detected by the Week 5 low-level-cue check and the seen/unseen tool split; mitigated by channel sim + RawBoost on training data.

- Kaggle 30 hr/week ceiling. Frozen-encoder-first, LoRA over full fine-tuning, parallel runs across three accounts; cut order: S3 ablations -> S2 -> never S1.

- AffectDF cross-eval turns out impractical (download size). Fallback: sampled subset; if still impractical, the pretrained-AASIST comparison row alone carries the external-validity claim.

- Conference deadline mismatch. Checked Week 10 Day 1; if the best venue closes early, swap Weeks 10–11 forward and push demo polish into Week 12.

- Twilio trial window / viva date. Trial activated Week 7 so the 30-day window covers Weeks 7–10; Rs 1–2k earmarked for pay-as-you-go if the viva falls outside it; WebRTC harness and Gradio as fallbacks; backup recording mandatory in Week 11.

# 7. One-liners the team should memorise

- Vs the base paper: "AffectDF measures the emotional gap and stops; we measure the code-mixing gap under telephony conditions, close it, and deploy it."

- On self-generated spoofs: "Held-out unseen tools, an external cross-evaluation on AffectDF, a pretrained-detector comparison row, and a low-level-cue sanity check — four independent defences."

- On scale: "They have 260 hours and H100 clusters; we have an untouched axis, a mitigation result, and a phone that beeps. Scale is their contribution; ours is the axis and the fix."