# 12-Week Project Plan

Code-Mixing Generalisation Gap in Audio Deepfake Detection + Live Call Detection Demo

B.Tech CSE (Data Science), Semester 7 - NMIMS School of Technology Management & Engineering

# 1. Team and roles

| Code | Member | Primary ownership |
| --- | --- | --- |
| L | M. Lahari (D006) | Data lead: corpora, preprocessing, channel simulation, spoof generation, dataset documentation, ethics/licence compliance |
| M | S. Mounika Reddy (D032) | Model lead: training pipeline, baseline, gap matrix, LoRA adaptation, ablations, experiment tracking |
| SK | K. Sai Krishna Reddy (D034) | Systems/demo lead: Twilio live-call pipeline, streaming inference, ONNX, dashboard, Gradio, deployment |
| ALL | Combined | Literature survey, paper writing, error analysis, report, presentation, viva preparation |

Roles are primary ownership, not silos - every task is reviewed by another member before merge. Writing in Weeks 9-12 is split by matching sections so each member owns roughly one third end to end.

# 2. How progress is tracked (GitHub workflow - mandatory)

Every task in this plan has a named owner and a named GitHub deliverable. Progress is not what someone says in a meeting; progress is what is merged.

- Branching: one branch per task, named week<N>/<member>-<short-task-name> (e.g. week2/lahari-channel-sim).

- Pull requests: every branch merges to main through a PR reviewed and approved by one other member. No direct pushes to main.

- Sunday deadline: each week's tasks are merged by Sunday night. The Monday 30-minute sync walks the GitHub Projects board: done / blocked / carried over.

- Evidence of progress each week = merged PRs + W&B run links (for training tasks) + one log-book entry per member. The log book is a department deliverable - 10 minutes weekly beats days of reconstruction in Week 12.

- Carried-over tasks are allowed but must be re-scheduled explicitly on the board with a reason; two consecutive carry-overs on the same task triggers a team re-plan of that area.

- Data and checkpoints never enter git (gitignored); they live on Kaggle Datasets/Drive with links + hashes committed instead.

# 3. Phase overview

| Weeks | Phase | Milestone |
| --- | --- | --- |
| 1-4 | Foundation & data: pipelines, spoof generation, dataset freeze | Dataset v1 frozen; baseline training started; Review 1 |
| 5-8 | Core research: baseline, gap matrix, adaptation, ablations + live-call system | Gap matrix at midterm (Review 2); results frozen; both demos work |
| 9-12 | Paper, polish, delivery | Paper submitted (Week 10); report + viva (Review 3) |

# 4. Week-by-week task plan

## Week 1 - Setup, datasets, accounts, approvals

Goal: Every dataset downloading, every account created, ethics cleared. Nothing blocks later weeks.

| ID | Owner | Task | Pushed to GitHub by Sunday |
| --- | --- | --- | --- |
| W1-T1 | L | Download and verify ASVspoof 2019 LA (Edinburgh DataShare, ~24 GB - the ONLY Stage-1 training corpus) and MUCS 2021 Hindi-English (openslr.org/104: 7.3 GB train + 443 MB test; skip Bengali-English files). | scripts/01_download_data.sh + data/manifests/download_report.md |
| W1-T2 | L | Download HiACC (Zenodo 15551669, 531 MB); extract ADULT subset only and quarantine child folders immediately. Set up HF streaming for IndicSynth (Hindi + Tamil), IndicTTS-Deepfake, IndicVoices subsets (eval-only). Skip ASVspoof 2021 DF (34.5 GB) unless college storage arrives. Draft per-corpus licence table (note IndicSynth CC-BY-NC, HiACC child exclusion). | docs/licences.md + docs/ethics/ (mentor sign-off scan) |
| W1-T3 | M | Create the GitHub repo with the agreed folder structure, requirements.txt, .gitignore, .env.example, and a CI lint check. Set up the GitHub Projects board with one card per task in this document. | Initial repo scaffold merged to main; Projects board live |
| W1-T4 | M | Verify Kaggle + Colab GPU environments: load wav2vec2-base, XLSR-53, WavLM-base and run a forward pass; create the W&B project; send the formal college GPU request email. | notebooks/env_check.ipynb + W&B project link in README |
| W1-T5 | SK | Build the free WebRTC dev harness (aiortc): two browsers join a call through the FastAPI server, server taps the audio. Do NOT activate Twilio yet (30-day trial is saved for Week 6). Set up ngrok. | live_call/webrtc_harness/ (rtc_server.py + call.html) |
| W1-T6 | SK | Study Twilio Conference + Media Streams docs and write the integration design note; create the HF account and a placeholder Space. | live_call/README.md (design note) + Space URL |
| W1-T7 | ALL | Each member deep-reads ~6 papers from the reference list and writes 3-4 sentence summaries (becomes the related-work section). Obtain mentor ethics/licence sign-off BEFORE any spoof generation. | docs/related_work_notes.md (3 PRs, one per member) |

Checkpoint: All datasets on disk or streaming; WebRTC harness passes audio browser-to-server-to-browser; mentor ethics sign-off committed.

## Week 2 - Preprocessing + channel simulation pipeline

Goal: The audio pipeline that everything downstream depends on.

| ID | Owner | Task | Pushed to GitHub by Sunday |
| --- | --- | --- | --- |
| W2-T1 | L | Build preprocessing: resample to 16 kHz mono, silero-vad trimming, loudness normalisation, 2-10 s segmentation. | src/data/preprocess.py + unit tests |
| W2-T2 | L | Build the channel simulation chain: 16 kHz to 8 kHz, AMR-NB or G.711 mu-law encode/decode, additive noise at 5/10/15/20 dB SNR, back to 16 kHz. Team listens to 20 samples. | src/data/channel_sim.py + tests/test_channel_sim.py + sample clips |
| W2-T3 | M | Define the manifest CSV format (filepath, label, language, speaker, tool, condition) and build the PyTorch Dataset + variable-length collate. | src/data/dataset.py |
| W2-T4 | M | Build the metrics module: EER, AUC-ROC, F1 with numpy bootstrap confidence intervals, verified against hand-computed toy cases. | src/training/metrics.py + tests/test_metrics.py |
| W2-T5 | SK | With L: select 30-50 adult speakers from MUCS + HiACC-adult (never child speakers, for anything) with >=30 s clean reference audio; extract code-mixed transcripts. With M: carve MUCS speakers into two DISJOINT pools (eval pool vs Stage-3 adaptation pool) before any generation. | data/manifests/speaker_pools.csv + selection criteria doc |
| W2-T6 | SK | Set up Coqui XTTS-v2 on Colab; generate 20 pilot clones; team rates quality in a shared sheet and agrees the quality bar. | notebooks/spoof_quality_audit.ipynb (pilot section) |

Checkpoint: Channel-sim output audibly telephony-grade; pilot clones judged usable; speaker pools frozen and disjoint.

## Week 3 - Spoof generation at scale + model scaffolding

Goal: The project-generated code-mixed spoof corpus - the core data contribution.

| ID | Owner | Task | Pushed to GitHub by Sunday |
| --- | --- | --- | --- |
| W3-T1 | L | Run XTTS-v2 generation at scale on Kaggle/Colab: 1,500-2,500 code-mixed utterances across selected adult speakers, logging tool, speaker ref, transcript and settings per file. | src/data/spoof_generation.py + generation metadata CSV |
| W3-T2 | L | Compile the manual quality audit: each member listens to a random 50-clip sample and tags failures; L writes the generation-quality statistics report (reviewers will ask). | notebooks/spoof_quality_audit.ipynb (final) + audit report |
| W3-T3 | M | Implement the model modules: encoder wrapper with freeze control, attentive statistics pooling, 2-layer MLP head, full detector. | src/models/ (encoder.py, pooling.py, classifier.py, detector.py) |
| W3-T4 | M | Implement the training loop (mixed precision, checkpointing, W&B logging) and smoke-test it on a 1% ASVspoof subset to confirm it learns. | src/training/train.py + W&B smoke-run link in PR |
| W3-T5 | SK | Set up Tortoise-TTS (firewalled from all training) and generate the 400-600 utterance unseen-attack split with separated metadata. | data/generated/heldout_tool/ metadata (audio stays off git) |
| W3-T6 | SK | Build the shared offline inference module: checkpoint + wav file in, probability + verdict out. Foundation for both demos. | src/inference/predict.py |

Checkpoint: Full spoof set generated with metadata; audit stats documented; training loop verified on subset.

## Week 4 - Dataset v1 freeze + baseline training starts

Goal: Evaluation corpus locked; English baseline underway.

| ID | Owner | Task | Pushed to GitHub by Sunday |
| --- | --- | --- | --- |
| W4-T1 | L | Assemble Dataset v1 per the dataset usage matrix: speaker-matched pairs, identical channel simulation on all eval audio (clean copies retained), manifests for all four columns (English / mono-Hindi / mono-Tamil / code-mixed). | src/data/build_manifests.py + data/manifests/*.csv |
| W4-T2 | L | Write the dataset datasheet: composition, sources, licences, generation process, exclusions (child audio, Tortoise firewall). | docs/datasheet.md |
| W4-T3 | M | Launch Stage-1 baseline fine-tuning on ASVspoof 2019 LA on Kaggle; iterate LR/schedule toward published EER ranges. Start early - multiple Kaggle sessions expected. | configs/train_baseline.yaml + W&B runs + checkpoints on Kaggle Datasets |
| W4-T4 | M | Implement the anti-leakage test suite (5 rules from the dataset matrix: speaker disjointness incl. cloned voices, Tortoise firewall, eval-only corpora, no child audio, transcript near-duplicates) and wire it into CI so it runs before every training launch. | tests/test_splits.py passing in CI |
| W4-T5 | SK | Build the FastAPI server skeleton: app structure, websocket echo endpoint, static file serving. | live_call/server.py (skeleton) |
| W4-T6 | SK | Build the streaming windowing prototype: rolling 4 s window / 2 s hop over a wav file played as a fake stream, per-window verdict. | src/inference/streaming.py |
| W4-T7 | ALL | Review 1 preparation (if scheduled): slides with dataset v1 statistics, pipeline diagram, pilot results. | report/presentation/review1.pptx |

Checkpoint: Dataset v1 FROZEN (changes only via changelog + team decision). Baseline training in progress.

## Week 5 - Baseline validated + streaming inference live

Goal: Trust the model before trusting any cross-lingual number.

| ID | Owner | Task | Pushed to GitHub by Sunday |
| --- | --- | --- | --- |
| W5-T1 | M | Finish baseline training; evaluate on ASVspoof held-out eval. GATE: EER must land in a defensible published range before anything downstream is trusted. | experiments/results/baseline.json + W&B report |
| W5-T2 | M | If EER is off: debug features, splits, pooling (contingency task - takes priority over everything). If EER is fine: begin LoRA config prep for Week 7. | Fix PRs or configs/train_lora_codemix.yaml draft |
| W5-T3 | L | Full evaluation-set QA pass: verify zero speaker overlap, uniform channel simulation, label balance per column; re-freeze as v1.1 with changelog if issues found. | docs/qa_report.md + CHANGELOG.md |
| W5-T4 | L | Prepare analysis slicing infrastructure: SNR bins, attack-tool tags, switch-density annotation for code-mixed utterances. | notebooks/eda_corpora.ipynb |
| W5-T5 | SK | Run streaming inference with exponential smoothing live over the WebRTC harness; record a short screen capture as proof. | Updated streaming.py + demo capture linked in PR |
| W5-T6 | SK | Export the model to ONNX with int8 quantisation; benchmark CPU latency per 4 s window (target < 1.5 s). | src/inference/export_onnx.py + benchmark table in README |
| W5-T7 | ALL | 30-minute mid-project risk review: baseline solid? Compute burn sustainable? Adjust Weeks 6-8 scope if needed; minutes committed. | docs/minutes/week5_risk_review.md |

Checkpoint: Validated English baseline with documented EER; streaming inference works on live WebRTC audio.

## Week 6 - THE GAP MATRIX (headline result) + Twilio goes live

Goal: The paper's central empirical claim, in hand by midterm.

| ID | Owner | Task | Pushed to GitHub by Sunday |
| --- | --- | --- | --- |
| W6-T1 | M | Run the English-trained model, unmodified, on all four eval columns in clean AND channel-matched conditions; compute EER/AUC/F1 per cell. | experiments/gap_matrix/ results JSONs |
| W6-T2 | M | Add bootstrap confidence intervals; produce the gap-matrix table and heatmap figure (publication quality). | experiments/figures/gap_matrix_heatmap.* |
| W6-T3 | L | Slice results by SNR, attack tool (seen XTTS vs unseen Tortoise), and corpus source; write up first findings. | Analysis section in notebooks/error_analysis.ipynb |
| W6-T4 | L | Begin the error-analysis notebook: which spoofs fool the detector, which genuine code-mixed clips get falsely flagged. | notebooks/error_analysis.ipynb |
| W6-T5 | SK | ACTIVATE the Twilio trial now (30-day window covers Weeks 6-9). Get the number, verify teammate phones, implement webhook -> Conference with Media Streams tap -> websocket -> streaming inference (port the WebRTC-proven code). Track the 75-minute budget from day one. | live_call/server.py + media_handler.py (Twilio path) |
| W6-T6 | SK | End-to-end real-call test: dial in, play recorded genuine and spoofed clips, log verdicts (terminal output is fine - no UI yet). | Verdict logs + short recording committed to docs/ |
| W6-T7 | ALL | Review 2 / midterm package: gap matrix v1 + live terminal demo of call verdicts. | report/presentation/review2.pptx |

Checkpoint: Gap matrix v1 exists - the central result is in hand. A real phone call gets classified live.

## Week 7 - LoRA adaptation + dashboard + in-call alerts

Goal: The gap-closure result plus the visible demo.

| ID | Owner | Task | Pushed to GitHub by Sunday |
| --- | --- | --- | --- |
| W7-T1 | M | Run LoRA / top-layer adaptation (PEFT) on the code-mixed adaptation split (disjoint MUCS pool + matching XTTS clones). | configs/train_lora_codemix.yaml + W&B runs + checkpoints |
| W7-T2 | M | Re-evaluate on held-out code-mixed data (clean + channel, seen + unseen); produce the before/after gap-closure table across ALL columns (verify English performance is not wrecked). | experiments/results/adaptation.json + table |
| W7-T3 | SK | Build the receiver dashboard: live call status, rolling verdict indicator (Real / Suspicious / Cloned), confidence meter, verdict timeline over websocket; plus the browser dialer page (Twilio Voice JS SDK). | live_call/static/dashboard.html + dialer.html + app.js |
| W7-T4 | SK | Build alert layer 1: Conference Participant API plays warning_beep.wav / whisper into the RECEIVER leg only when the verdict crosses threshold. | live_call/alerts.py + audio_assets/ |
| W7-T5 | L | Curate the demo audio arsenal: 10-15 clips (genuine, XTTS clone, Tortoise clone), each verified through the full Twilio path; document surprises as error-analysis material. | demo_assets/ + verification sheet |
| W7-T6 | L | Select the live-demo operating threshold from the DET curve (favour low false-alarms on genuine speech) and document the decision; ALL sign off in the weekly sync. | configs/threshold.yaml + docs/minutes/threshold_decision.md |

Checkpoint: Adaptation numbers final-draft quality; a live Twilio call shows a beep in the receiver's ear + red dashboard.

## Week 8 - Ablations, alert escalation, results freeze

Goal: Everything the paper needs, locked; both demos functional.

| ID | Owner | Task | Pushed to GitHub by Sunday |
| --- | --- | --- | --- |
| W8-T1 | M | Primary ablation: frozen vs fine-tuned encoder; secondary (wav2vec2 vs WavLM) only if Kaggle hours allow. | experiments/results/ablations.json |
| W8-T2 | M | Consolidate final results tables and publication figures (DET curves, heatmap, adaptation deltas). | experiments/figures/ complete set |
| W8-T3 | L | Complete error analysis by switch density, SNR, utterance length, attack tool - written directly as draft paper text. | paper/sections/analysis.tex |
| W8-T4 | L | Finalise the dataset datasheet as the paper appendix / supplementary material. | paper/supplementary/datasheet.pdf source |
| W8-T5 | SK | Build the escalation ladder in verdict_engine: first detection = beep + red dashboard; sustained 10 s = repeat beep + SMS alert; call end = summary SMS + log, always. Decide now: if the viva date falls after trial expiry, upgrade Twilio pay-as-you-go from the Rs 1-2k budget. | live_call/verdict_engine.py + SMS templates |
| W8-T6 | SK | Build and deploy the Gradio upload/record demo on HF Spaces (reuses predict.py); deploy the call server to a persistent host; add reconnect and call-end handling. | demo/app.py + live Space URL + deployment notes |
| W8-T7 | ALL | Results freeze meeting: these are the paper's numbers. Later reruns only for bug fixes, logged in the changelog. | CHANGELOG.md freeze entry + minutes |

Checkpoint: All experimental results frozen. Live-call demo AND Gradio demo functional.

## Week 9 - Paper draft

Goal: Full IEEE-format draft, internally reviewed once.

| ID | Owner | Task | Pushed to GitHub by Sunday |
| --- | --- | --- | --- |
| W9-T1 | L | Write: Dataset & Corpus Construction, Channel-Matched Protocol, Ethics/Licence statement. | paper/sections/ (L's sections) via Overleaf-synced repo |
| W9-T2 | M | Write: Methodology (model + training stages), Experiments & Results, all figures/tables placed. | paper/sections/ (M's sections) |
| W9-T3 | SK | Write: Introduction, Related Work (from Week-1 summaries), System & Deployment (live telephony detection - the evaluation protocol deployed), Conclusion & Future Work. | paper/sections/ (SK's sections) |
| W9-T4 | M | Start REPRODUCE.md: configs + seeds + commands that regenerate every paper table from checkpoints. | REPRODUCE.md (draft) |
| W9-T5 | ALL | Venue shortlist: 2-3 legitimate Scopus-indexed conferences (INDICON/TENCON-class or Springer speech/AI venues); check submission deadlines DAY 1 and reorder Weeks 9-10 if a deadline forces it; predatory venues excluded. | docs/venues.md |
| W9-T6 | ALL | Cross-review: each member reviews both others' sections via PR comments; one full integration pass. | Review comments resolved; paper/main.tex compiles |

Checkpoint: Complete draft in Overleaf/repo, internally reviewed once.

## Week 10 - Paper submission + demo polish

Goal: Rubric tier 2 secured: submitted, under 10% similarity.

| ID | Owner | Task | Pushed to GitHub by Sunday |
| --- | --- | --- | --- |
| W10-T1 | ALL | Revision pass with mentor feedback; plagiarism/AI-similarity check; fix; SUBMIT to the chosen venue. This is the week's non-negotiable outcome. | Submission receipt in docs/ + tagged paper version |
| W10-T2 | SK | Demo polish: dashboard styling; rehearsed 3-minute script (dial - genuine clip - Real - clone - beep in the ear - red dashboard - escalation SMS - post-call summary). | docs/viva/demo_script.md |
| W10-T3 | SK | Record the backup demo screen-recording WITH audio of a full successful run (networks fail at vivas; the recording never does). | Recording link in docs/viva/ (file on Drive) |
| W10-T4 | L | Final licence/ethics documentation package + public README for the dataset artefact. | docs/licences.md final + dataset README |
| W10-T5 | L | Verify Twilio spend vs budget; top up from Rs 1-2k only if trial credit exhausted; document costs for the report. | docs/budget.md |
| W10-T6 | M | Finish REPRODUCE.md end-to-end (fresh-clone test on a teammate's machine); tag release v1.0. | REPRODUCE.md final + git tag v1.0 |

Checkpoint: PAPER SUBMITTED. Demo runs clean start-to-finish; backup recording exists.

## Week 11 - Final evaluation matrix + viva material

Goal: Everything frozen, viva-grade.

| ID | Owner | Task | Pushed to GitHub by Sunday |
| --- | --- | --- | --- |
| W11-T1 | M | Final full evaluation matrix (all columns x clean/channel x seen/unseen) from frozen checkpoints. | experiments/results/final_matrix.json + tables |
| W11-T2 | M | Final model freeze; archive all checkpoints to Kaggle Datasets/Drive with hashes. | Checkpoint archive links + hashes in docs/ |
| W11-T3 | L | Failure-case exhibit for the viva: 5-6 curated examples (audio + model output + explanation) showing successes AND honest failures. | docs/viva/failure_cases.md + clips |
| W11-T4 | SK | Full demo dress rehearsal x3 with the whole team; file and close an issue for every flaky behaviour found. | Closed GitHub issues + rehearsal notes |
| W11-T5 | SK | Confirm the HF Spaces Gradio link is public and stable; finalise the backup recording. | Status note + final recording |
| W11-T6 | ALL | Department report skeleton in the institute template; drop in paper content reformatted to department structure; assemble log-book entries to date. | report/report_draft.docx (~50%) + report/logbook/ |

Checkpoint: Final numbers locked; demo bulletproof; report ~50% assembled.

## Week 12 - Report, presentation, viva

Goal: Review 3 delivery.

| ID | Owner | Task | Pushed to GitHub by Sunday |
| --- | --- | --- | --- |
| W12-T1 | L | Report chapters: Introduction, Literature Survey, Dataset & Methodology (data half); compile and format the complete log book. | report/ chapters + logbook final |
| W12-T2 | M | Report chapters: Methodology (model half), Results & Analysis, all figures and tables. | report/ chapters |
| W12-T3 | SK | Report chapters: System Design & Implementation (with the live-call architecture diagram), Conclusion & Future Work; build the final presentation deck (each member presents their own third). | report/ chapters + report/presentation/final.pptx |
| W12-T4 | ALL | Viva rehearsal x2 using the anticipated-questions list, including: 'Why is live telephony no longer out of scope?' - because Twilio Media Streams delivers exactly the 8 kHz telephony audio the channel-matched protocol was designed for; the demo IS the evaluation protocol, deployed. | docs/viva/qa_prep.md |
| W12-T5 | ALL | Final report assembly, print, and hard-bound submission. | Final report PDF committed |
| W12-T6 | ALL | Repo cleanup: remove dead branches, final README, tag v1.0-final. | git tag v1.0-final |

Checkpoint: Review 3 done. Project complete.

# 5. Workload balance

| Member | Technical core (Weeks 1-8) | Writing core (Weeks 9-12) |
| --- | --- | --- |
| L | Data pipeline, channel sim, spoof generation, dataset freeze, QA, error analysis, demo arsenal, thresholds | Dataset/protocol/ethics paper sections; report intro + literature + data chapters; log book |
| M | Training infra, baseline, gap matrix, LoRA, ablations, final matrices, leakage tests | Method/results sections + figures; report results chapters; reproducibility |
| SK | WebRTC harness, Twilio pipeline, streaming + ONNX, dashboard, alerts, Gradio, deployment | Intro/related-work/system sections; report system chapter; presentation deck |

# 6. Top risks (12-week version)

- Baseline does not reproduce (Week 5): the gap-matrix run itself is cheap - only training is expensive. If baseline slips one week, compress Week 8 to the single primary ablation.

- Conference deadline mismatch: check deadlines on Week 9 Day 1; if the best venue closes early, swap Weeks 9-10 forward and push demo polish to Week 11.

- Twilio flakiness at the viva: mitigated by the mandatory backup recording (Week 10), the free WebRTC harness as a live fallback (same detection pipeline), and the Gradio demo as a third fallback.

- Twilio 30-day trial expiry / 75-minute cap: trial activated only in Week 6 so the window covers Weeks 6-9; all earlier development on the free WebRTC harness; short dev calls; Rs 1-2k earmarked for a pay-as-you-go upgrade in Week 8 if the viva falls outside the window.

- Kaggle 30 hr/week ceiling: frozen-encoder-first, LoRA instead of full fine-tuning, and parallel independent runs across all three members' Kaggle accounts.